## Sheet1
Unique ID | User story front end implementation | Story points | Assignee | Reviewer 1 | Reviewer 2
1.01 | As an investor I should be able to fill an application form, so that I can establish a company. | 5 | Lujine | Hosam | Mostafa
1.02 | As an investor I should have the option to choose a company type I want to establish, so that I can be directed accordingly to the appropriate application form. | 2 | Mohamed Ayman | Omar | Ahmed El-Sherif
1.03 | As an investor I should be able to update the form, so that I can fix any incorrect entries and continue the process. | 5 | Mostafa | Adel | Farid
1.05 | As an investor I should be able to resend the rejected form after update, so that I can continue the process. | 3 | Omar | Farid | Mohamed Ayman
1.06 | As an investor I should be able to view a list of my current or pending companies, so that I can access their details. | 2 | Adel | Mark | Hosam
1.07 | As an investor I should be able to change the website's language between English and Arabic, so that I can have easy access in my preferred language. | 5 | Ahmed El-Sherif | Mostafa | Mark
1.08 | As an investor I should be able to cancel an unreviewed application, so that I can stop the process of establishing a company I don't want anymore. | 3 | Mohamed Ayman | Omar | Ahmed El-Sherif
1.09 | As an investor I should be able to pay the fees, so that I can complete the process and establish my company. | 2 | Hosam | Lujine | Yasser
2.01 | As an investor I should be able to receive notifications regarding my application, so that I can take the next action. | 5 | Yasser | Ahmed El-Sherif | Adel
4.02 | As a reviewer I should be able to add comments on rejected forms, so that the lawyers can know what to update. | 5 | Omar | Farid | Mohamed Ayman
4.03 | As a reviewer I should be able to preview (read only) applications, so that I can decide whether to accept or reject | 2 | Hosam | Lujine | Yasser
4.04 | As a lawyer I should be able to fill forms delegated to me by an investor, so that the investor can apply via GAFI with the lawyer's help. | 5 | Lujine | Hosam | Mostafa
4.05 | As a lawyer I should be able to review forms filled by an investor, so that I can ensure their validity. | 2 | Hosam | Lujine | Yasser
4.06 | As a lawyer I should be able to accept or reject forms filled by the investor, so that further action can be taken. | 2 | Hosam | Lujine | Yasser
4.07 | As an admin I should be able to publish established companies details on portal, so that their details are available online. | 2 | Yasser | Ahmed El-Sherif | Adel
4.1 | As a lawyer I should be able to edit forms declined by the reviewer and regenerate documents, so that I can update the forms and continue with the process. | 3 | Mostafa | Adel | Farid
4.12 | As a lawyer I should be able to (re)calculate fees so that the investor can know the amount to pay. | 3 | Farid | Mohamed Ayman | Lujine
5.01 | As an investor I should be able to login to my page so I can use the website features | 2 | Mohamed Ayman | Omar | Ahmed El-Sherif
5.02 | As an internal user I should be able to log in to the internal portal so that I can work on my tasks | 2 | Mohamed Ayman | Omar | Ahmed El-Sherif
5.04 | As an admin I should be able to register employees and assign them to specific departments, so that I can maintain the workflow of the institution. | 2 | Farid | Mohamed Ayman | Lujine
5.06 | As a user I should be able update my profile, so that I can change my personal details. | 3 | Mark | Yasser | Omar
6.01 | As an Internal User I should have a Work page which lists the tasks due for me as a logged in user so that I can perform my work tasks | 2 | Ahmed El-Sherif | Mostafa | Mark
6.02 | As an Internal User I should be able to view all the cases in the system so that I can open them and check their details | 2 | Ahmed El-Sherif | Mostafa | Mark
6.03 | As an Internal User I should be able to sort my tasks by "Case ID", or "Case Creation Date" so that I can find specific tasks and prioritize my work | 3 | Ahmed El-Sherif | Mostafa | Mark
6.05 | As an Internal User I can see who last worked on a case so that we can all be updated of each other's work | 2 | Omar | Farid | Mohamed Ayman
Estimation Report
| Sprint | Total Velocity | Average Velocity
| Sprint 1 | 11.2803 | 1.13
| Sprint 2 | 6.9259 | 0.61151
| Speed up ratio - I | 0.61398 | 0.54116
| Sprint 4 | 2.3863 | 0.22857
| Sprint 5 team estimated Velocity | 1.4651 | 0.12369