## Sheet1
User story | Story Points | Assignee | Depends on | Testing User Story?
Investor
Create | 3 | Mohamed Ayman
Read | 3 | Mohamed Farid | Create | Creating then viewing an investor
Update | 3 | Mohamed Ayman
Delete | 2 | Mohamed Farid | Create | Creating then deleting an investor
Admin
Create | 3 | Lujine
Read | 3 | Mohamed Hosam | Create | Creating then viewing an admin
Update | 3 | Lujine
Delete | 2 | Mohamed Hosam | Create | Creating then deleting an admin
Lawyer
Create | 3 | Mohamed Yasser
Read | 3 | Mohamed Adel | Create | Creating then viewing a lawyer
Update | 3 | Mohamed Yasser
Delete | 2 | Mohamed Adel | Create | Creating then deleting a lawyer
Reviewer
Create | 3 | Omar Ayman
Read | 3 | Mostafa | Create | Creating then viewing a reviewer
Update | 3 | Omar Ayman
Delete | 2 | Mostafa | Create | Creating then deleting a reviewer
External Entity
Create | 3 | Ahmed El-Sherif
Read | 3 | Mark | Create | Creating then viewing an external entity
Update | 3 | Ahmed El-Sherif
Delete | 2 | Mark | Create | Creating then deleting an external entity
Company
Create | 3 | Mohamed Adel
Read | 3 | Lujine | Create | Creating then viewing a company
Update | 3 | Mohamed Adel
Delete | 2 | Lujine | Create | Creating then deleting a company
Task
Create | 3 | Mohamed Yasser
Read | 3 | Mohamed Hosam | Create | Creating then viewing a task
Update | 3 | Mohamed Yasser
Delete | 2 | Mohamed Hosam | Create | Creating then deleting a task