## Sheet1
Unique ID | User story front end implementation | Story points | Assignee | Reviewer 1 | Reviewer 2
4.01 | As a reviewer I should be able to accept or reject an application, so that the application goes to the next stage or go back to the updating stage accordingly. | 2 | Hosam | Lujine | Yasser
1.04 | As an investor I should be able to view rejected forms with the lawyer's comments, so that I can know which data to update. | 5 | Lujine | Hosam | Mostafa
4.11 | As a lawyer I should be able to send back rejected forms attached with comments to the investor, so that they can be updated appropriately. | 3 | Omar | Farid | Mohamed Ayman
4.09 | As an admin I should be able to search through all cases so that I can see their details. | 5 | Mostafa | Adel | Farid
7.02 | As a registered/unregistered user I should be able to see approved companies' E-journals so I can know information about them | 3 | Adel | Mark | Hosam
5.02 | As an internal user I should be able to log in to the internal portal so that I can work on my tasks | 2 | Mohamed Ayman | Omar | Ahmed El-Sherif
5.03 | As an investor I should be able to register to the website so that I can join the portal and be able to establish my own companies | 3 | Farid | Mohamed Ayman | Lujine
5.05 | As an admin I should be able to delete/deactivate the account of the employees who leave GAFI, so that I can prevent unauthorized access. | 3 | Ahmed El-Sherif | Mostafa | Mark
3.04 | As an investor I should be able to see an FAQ page so that it can help me understand how the website works | 3 | Yasser | Ahmed El-Sherif | Adel
3.01 | As an investor I should be able to keep track of my application, so that I can see which state my application is at. | 3 | Mark | Yasser | Omar