## Copy of Sheet1
Unique ID | User story | Story Points | Assignee | Reviewer 1 | Reviewer 2 | Unique id is with refrence to original product backlog
4.01 | As a reviewer I should be able to accept or reject an application, so that the application goes to the next stage or go back to the updating stage accordingly. | 2 | Lujine | Ayman | Shiko
1.01 | As an investor I should be able to fill an application form, so that I can establish a company. | 5 | Adel | Shiko | Lujine
1.04 | As an investor I should be able to view rejected forms with the lawyer's comments, so that I can know which data to update. | 3 | Hosam | Lujine | Omar
3.01 | As an investor I should be able to keep track of my application, so that I can see which state my application is at. | 3 | Farid | Adel | Yasser
4.03 | As a reviewer I should be able to preview (read only) applications, so that I can decide whether to accept or reject | 2 | Ayman | Mostafa | Mark
4.05 | As a lawyer I should be able to review forms filled by an investor, so that I can ensure their validity. | 3 | Mark | Omar | Hosam
4.06 | As a lawyer I should be able to accept or reject forms filled by the investor, so that further action can be taken. | 3 | Yasser | Farid | Adel
4.04 | As a lawyer I should be able to fill forms delegated to me by an investor, so that the investor can apply via GAFI with the lawyer's help. | 5 | Mostafa | Mark | Farid
1.03 | As an investor I should be able to update the form, so that I can fix any incorrect entries and continue the process. | 5 | Mostafa | Mark | Farid
4.02 | As a reviewer I should be able to add comments on rejected forms, so that the lawyers can know what to update. | 3 | Farid | Adel | Yasser
6.01 | As an Internal User I should have a Work page which lists the tasks due for me as a logged in user so that I can perform my work tasks | 5 | Yasser | Farid | Adel
6.02 | As an Internal User I should be able to view all the cases in the system so that I can open them and check their details | 3 | Ayman | Mostafa | Mark
4.07 | As an admin I should be able to publish established companies details on portal, so that their details are available online. | 5 | Hosam | Lujine | Omar
1.06 | As an investor I should be able to view a list of my current or pending companies, so that I can access their details. | 3 | Adel | Shiko | Lujine
4.08 | As an admin I should be able to assign due dates to specific tasks, so that I can follow up with my employees. | 5 | Shiko | Yasser | Ayman
4.09 | As an admin I should be able to search through all cases so that I can see their details. | 3 | Mark | Omar | Hosam
4.1 | As a lawyer I should be able to edit forms declined by the reviewer and regenerate documents, so that I can update the forms and continue with the process. | 5 | Omar | Hosam | Mostafa
4.11 | As a lawyer I should be able to send back rejected forms attached with comments to the investor, so that they can be updated appropriately. | 3 | Lujine | Ayman | Shiko
6.04 | As an Internal User I should be able to view tasks assigned to my department, so that I can be aware of coworkers updates. | 3 | Shiko | Yasser | Ayman
Mongo DB Addition
| Investor | 2 | Mostafa | Yasser | Adel
| Admin | 2 | Farid | Yasser | Adel
| Lawyer | 2 | Omar | Lujine | Adel
| Reviewer | 2 | Hosam | Lujine | Adel
| External Entity | 2 | Ayman | Lujine | Yasser
| Task | 2 | Mark | Lujine | Yasser
| Company | 2 | Shiko | Lujine | Yasser
| CompanyType | 5 | Lujine | Mark | Mostafa
| Heroku Addition |  | Mark | Mostafa | Farid