## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
Investor
| Create | 3 | Mohamed Ayman
| Read | 3 | Mohamed Farid | Create | Creating then viewing an investor
| Update | 3 | Mohamed Ayman
| Delete | 2 | Mohamed Farid | Create | Creating then deleting an investor
Admin
| Create | 3 | Lujine
| Read | 3 | Mohamed Hosam | Create | Creating then viewing an admin
| Update | 3 | Lujine
| Delete | 2 | Mohamed Hosam | Create | Creating then deleting an admin
Lawyer
| Create | 3 | Mohamed Yasser
| Read | 3 | Mohamed Adel | Create | Creating then viewing a lawyer
| Update | 3 | Mohamed Yasser
| Delete | 2 | Mohamed Adel | Create | Creating then deleting a lawyer
Reviewer
| Create | 3 | Omar Ayman
| Read | 3 | Mostafa | Create | Creating then viewing a reviewer
| Update | 3 | Omar Ayman
| Delete | 2 | Mostafa | Create | Creating then deleting a reviewer
External Entity
| Create | 3 | Ahmed El-Sherif
| Read | 3 | Mark | Create | Creating then viewing an external entity
| Update | 3 | Ahmed El-Sherif
| Delete | 2 | Mark | Create | Creating then deleting an external entity
Form
| Create | 3 | Mohamed Farid
| Read | 3 | Omar Ayman | Create | Creating then viewing a form
| Update | 3 | Mohamed Farid
| Delete | 2 | Omar Ayman | Create | Creating then deleting a form
Company
| Create | 3 | Mohamed Adel
| Read | 3 | Lujine | Create | Creating then viewing a company
| Update | 3 | Mohamed Adel
| Delete | 2 | Lujine | Create | Creating then deleting a company
Task
| Create | 3 | Mohamed Yasser
| Read | 3 | Mohamed Hosam | Create | Creating then viewing a task
| Update | 3 | Mohamed Yasser
| Delete | 2 | Mohamed Hosam | Create | Creating then deleting a task