## CRUDs Unit tests
Jest unit tests | Story Points | Assignee | Reviewer 1 | Reviewer 2
Investor
Create | 3 | Mohamed Ayman | Ahmed El-Sherif | Mark
Read | 2 | Farid | Ahmed El-Sherif | Mark
Update | 3 | Mohamed Ayman | Ahmed El-Sherif | Mark
Delete | 2 | Farid | Ahmed El-Sherif | Mark
Admin
Create | 3 | Lujine | Farid | Mohamed Yasser
Read | 2 | Mohamed Hosam | Farid | Mohamed Yasser
Update | 3 | Lujine | Farid | Mohamed Yasser
Delete | 2 | Mohamed Hosam | Farid | Mohamed Yasser
Lawyer
Create | 3 | Mohamed Yasser | Mohamed Ayman | Lujine
Read | 2 | Mohamed Adel | Mohamed Ayman | Lujine
Update | 3 | Mohamed Yasser | Mohamed Ayman | Lujine
Delete | 2 | Mohamed Adel | Mohamed Ayman | Lujine
Reviewer
Create | 3 | Omar Ayman | Mohamed Adel | Farid
Read | 2 | Mostafa | Mohamed Adel | Farid
Update | 3 | Omar Ayman | Mohamed Adel | Farid
Delete | 2 | Mostafa | Mohamed Adel | Farid
External Entity
Create | 3 | Ahmed El-Sherif | Mohamed Yasser | Omar Ayman
Read | 2 | Mark | Mohamed Yasser | Omar Ayman
Update | 3 | Ahmed El-Sherif | Mohamed Yasser | Omar Ayman
Delete | 2 | Mark | Mohamed Yasser | Omar Ayman
Company
Create | 3 | Mohamed Adel | Mohamed Hosam | Ahmed El-Sherif
Read | 2 | Lujine | Mohamed Hosam | Ahmed El-Sherif
Update | 3 | Mohamed Adel | Mohamed Hosam | Ahmed El-Sherif
Delete | 2 | Lujine | Mohamed Hosam | Ahmed El-Sherif
Task
Create | 3 | Mohamed Yasser | Mostafa | Mark
Read | 2 | Mohamed Hosam | Mostafa | Mark
Update | 3 | Mohamed Yasser | Mostafa | Mark
Delete | 2 | Mohamed Hosam | Mostafa | Mark
CompanyType
Create | 3 | Lujine | Omar Ayman | Mohamed Hosam
Read | 2 | Mostafa | Omar Ayman | Mohamed Hosam
Update | 3 | Lujine | Omar Ayman | Mohamed Hosam
Delete | 2 | Mostafa | Omar Ayman | Mohamed Hosam

## User stories Unit tests
Unique ID | Jest unit tests | Story Points | Assignee | Reviewer 1 | Reviewer 2
4.01 | As a reviewer I should be able to accept or reject an application, so that the application goes to the next stage or go back to the updating stage accordingly. | 2 | Lujine | Mohamed Ayman | Ahmed El-Sherif
1.01 | As an investor I should be able to fill an application form, so that I can establish a company. | 3 | Adel | Ahmed El-Sherif | Lujine
1.04 | As an investor I should be able to view rejected forms with the lawyer's comments, so that I can know which data to update. | 2 | Hosam | Lujine | Omar
3.01 | As an investor I should be able to keep track of my application, so that I can see which state my application is at. | 2 | Farid | Adel | Yasser
4.03 | As a reviewer I should be able to preview (read only) applications, so that I can decide whether to accept or reject | 2 | Mohamed Ayman | Mostafa | Mark
4.05 | As a lawyer I should be able to review forms filled by an investor, so that I can ensure their validity. | 2 | Mark | Omar | Hosam
4.06 | As a lawyer I should be able to accept or reject forms filled by the investor, so that further action can be taken. | 2 | Yasser | Farid | Adel
4.04 | As a lawyer I should be able to fill forms delegated to me by an investor, so that the investor can apply via GAFI with the lawyer's help. | 3 | Mostafa | Mark | Farid
1.03 | As an investor I should be able to update the form, so that I can fix any incorrect entries and continue the process. | 3 | Mostafa | Mark | Farid
4.02 | As a reviewer I should be able to add comments on rejected forms, so that the lawyers can know what to update. | 2 | Farid | Adel | Yasser
6.01 | As an Internal User I should have a Work page which lists the tasks due for me as a logged in user so that I can perform my work tasks | 2 | Yasser | Farid | Adel
6.02 | As an Internal User I should be able to view all the cases in the system so that I can open them and check their details | 2 | Mohamed Ayman | Mostafa | Mark
4.07 | As an admin I should be able to publish established companies details on portal, so that their details are available online. | 2 | Hosam | Lujine | Omar
1.06 | As an investor I should be able to view a list of my current or pending companies, so that I can access their details. | 2 | Adel | Ahmed El-Sherif | Lujine
4.08 | As an admin I should be able to assign due dates to specific tasks, so that I can follow up with my employees. | 2 | Ahmed El-Sherif | Yasser | Mohamed Ayman
4.09 | As an admin I should be able to search through all cases so that I can see their details. | 2 | Mark | Omar | Hosam
4.1 | As a lawyer I should be able to edit forms declined by the reviewer and regenerate documents, so that I can update the forms and continue with the process. | 3 | Omar | Hosam | Mostafa
4.11 | As a lawyer I should be able to send back rejected forms attached with comments to the investor, so that they can be updated appropriately. | 2 | Lujine | Mohamed Ayman | Ahmed El-Sherif
6.04 | As an Internal User I should be able to view tasks assigned to my department, so that I can be aware of coworkers updates. | 2 | Ahmed El-Sherif | Yasser | Mohamed Ayman

## New user stories
Unique ID | User story | Story Points | Assignee | Reviewer 1 | Reviewer 2
1.08 | As an investor I should be able to cancel an unreviewed application, so that I can stop the process of establishing a company I don't want anymore. | 3 | Ahmed El-Sherif | Mostafa | Hosam
1.09 | As an investor I should be able to pay the fees, so that I can complete the process and establish my company. | 5 | Mostafa | Adel | Farid
2.04 | As an admin I should be able to view the investors' feedback so that I can make the right improvements to the service | 3 | Hosam | Lujine | Yasser
3.02 | As an investor I should be able to read a description of the form, so that I can understand what to fill in each field. | 3 | Omar | Farid | Mohamed Ayman
3.03 | As an investor I should be able to review the online service and give suggestions, so that the service can be improved. | 2 | Yasser | Hosam | Ahmed El-Sherif
4.12 | As a lawyer I should be able to (re)calculate fees so that the investor can know the amount to pay. | 3 | Farid | Mohamed Ayman | Lujine
6.05 | As an Internal User I can see who last worked on a case so that we can all be updated of each other's work | 2 | Mohamed Ayman | Omar | Adel
7.02 | As a registered/unregistered user I should be able to see approved companies' E-journals so I can know information about them | 2 | Adel | Mark | Hosam
5.06 | As a user I should be able to update my profile, so that I can change my personal details. | 2 | Mark | Yasser | Omar